## Capital Plan 2027
AURORA RIDGE ENERGY (FICTIONAL COMPANY) — CAPITAL INVESTMENT PLAN 2027
Synthetic demonstration data: all names, projects and amounts are invented.
USD thousands
Project | [6 empty] | Plan by month | [11 empty] | Plan by quarter |  |  |  | Plan 2027 | Actual by month | [11 empty] | Performance |  |  |  | Internal |  | Comments
No. | Project | Business unit | Category | Priority | Project manager | Contract status | Plan Jan | Plan Feb | Plan Mar | Plan Apr | Plan May | Plan Jun | Plan Jul | Plan Aug | Plan Sep | Plan Oct | Plan Nov | Plan Dec | Q1 | Q2 | Q3 | Q4 | Annual plan | Actual Jan | Actual Feb | Actual Mar | Actual Apr | Actual May | Actual Jun | Actual Jul | Actual Aug | Actual Sep | Actual Oct | Actual Nov | Actual Dec | Actual YTD | Full-year forecast | Variance vs plan | Completion, % | Prior-year actual | Helper code | Comments
1 | UPSTREAM — HARBOR BASIN FIELDS | [5 empty] | 231 | 340.4 | 557.8 | 882.1 | 1122.5 | 1407.8 | 1298.6 | 1628.1 | 1522.6 | 1654.5 | 1559.5 | 1477.1 | 1129.2 | 3412.4 | 4449.3 | 4691.1 | 13682 | 223.4 | 272.5 | 536 | 753.6 | 841 | 1253.7 | 1101.8 | 1336.1 | 1190.1 | 71 | 29.4 | 55.3 | 7663.9 | 12406.6 | -1275.4 | 56.01% | 11025.8
1.1 | Development drilling | [5 empty] | 124.1 | 218.6 | 359.4 | 514.7 | 563.6 | 599.7 | 565.1 | 871.7 | 727.4 | 814.7 | 721.5 | 750.4 | 702.1 | 1678 | 2164.2 | 2286.6 | 6830.9 | 126.3 | 149.4 | 346.5 | 407.6 | 413.6 | 434 | 517.5 | 731.4 | 601 | 37.3 | 20.8 | 39.5 | 3824.9 | 6169.5 | -661.4 | 55.99% | 6528.5
1.1.1 | Overhaul of well pad P-109 | Harbor Basin | Capex | High | Manager 12 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-101-109
1.1.2 | New well HB-114 | Harbor Basin | Capex | Medium | Manager 18 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.3 | 20.8 | 39.5 | 97.6 | 130.7 | 130.7 | 0% | 0 | WBS-101-114
1.1.3 | Study for sidetrack HB-122S | Cedar Point | Capex | Low | Manager 16 | Signed | 0 | 0 | 0 | 0 | 193.7 | 93.8 | 64.9 | 169.2 | 201.2 | 81.5 | 158.6 | 197.3 | 0 | 287.5 | 435.3 | 437.4 | 1160.2 | 0 | 0 | 0 | 0 | 123.2 | 75.8 | 59.7 | 154 | 210 | 0 | 0 | 0 | 622.7 | 1099.4 | -60.8 | 53.67% | 1232.1 | WBS-101-122 | Design approved; construction starts after the rainy season.
1.1.4 | Expansion of well pad P-131 | Harbor Basin | Capex | Low | Manager 19 | Signed | 0 | 0 | 0 | 0 | 21.8 | 31.2 | 36.7 | 52.4 | 59.4 | 47.3 | 67.1 | 68.9 | 0 | 53 | 148.5 | 183.3 | 384.8 | 0 | 0 | 0 | 0 | 20.2 | 31.3 | 20.7 | 45.1 | 41.5 | 0 | 0 | 0 | 158.8 | 323 | -61.8 | 41.27% | 122.9 | WBS-101-131 | Permit pending; spending moved to the second half of the year.
1.1.5 | Replacement of well pad P-139 | Cedar Point | Capex | High | Manager 20 | Planned | 0 | 0 | 167.3 | 222.6 | 130.2 | 189.9 | 72.5 | 211.6 | 158.7 | 231.4 | 89.2 | 174.9 | 167.3 | 542.7 | 442.8 | 495.5 | 1648.3 | 0 | 0 | 139 | 137.3 | 124.1 | 137.5 | 61.2 | 139.7 | 115.9 | 0 | 0 | 0 | 854.7 | 1289 | -359.3 | 51.85% | 1289.2 | WBS-101-139
1.1.6 | Study for well pad P-140 | Corporate | Capex | High | Manager 14 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-101-140
1.1.7 | Overhaul of well HB-148 | Eastgate | Capex | High | Manager 14 | Tender | 103.4 | 61.1 | 40 | 88.6 | 112.1 | 91.7 | 68.5 | 130.8 | 44.3 | 132.4 | 107.9 | 67.6 | 204.5 | 292.4 | 243.6 | 307.9 | 1048.4 | 105.4 | 40.2 | 45.8 | 94.9 | 75.1 | 52.1 | 48.2 | 78.5 | 24.5 | 0 | 0 | 0 | 564.7 | 862 | -186.4 | 53.86% | 1305.2 | WBS-101-148 | Contractor mobilised; schedule confirmed with operations.
1.1.8 | Overhaul of well pad P-149 | Corporate | Capex | Medium | Manager 07 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-101-149 | Deferred: waiting for partner approval.
1.1.9 | Replacement of sidetrack HB-156S | Corporate | Capex | Medium | Manager 17 | Planned | 20.7 | 18.7 | 22.5 | 19.1 | 13.3 | 14.2 | 31.9 | 31.3 | 30.8 | 22.3 | 16.3 | 14.1 | 61.9 | 46.6 | 94 | 52.7 | 255.2 | 20.9 | 18.3 | 20 | 17.4 | 9.4 | 13.6 | 30.8 | 32.7 | 32.4 | 0 | 0 | 0 | 195.5 | 256 | 0.8 | 76.61% | 372.2 | WBS-101-156
1.1.10 | Upgrade of well pad P-161 | Eastgate | Capex | Low | Manager 07 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-101-161
1.1.11 | New well HB-162 | Corporate | Capex | Low | Manager 20 | Planned | 0 | 0 | 0 | 0 | 0 | 55.3 | 66 | 59.1 | 62.9 | 36.3 | 37.4 | 58.8 | 0 | 55.3 | 188 | 132.5 | 375.8 | 0 | 0 | 0 | 0 | 0 | 33.3 | 68.8 | 66.1 | 49.1 | 0 | 0 | 0 | 217.3 | 332.9 | -42.9 | 57.82% | 515.5 | WBS-101-162
1.1.12 | Upgrade of sidetrack HB-171S | Cedar Point | Capex | High | Manager 02 | In negotiation | 0 | 0 | 0 | 0 | 8.5 | 10.8 | 11.8 | 17.6 | 10.7 | 24.9 | 29.5 | 13.2 | 0 | 19.3 | 40.1 | 67.6 | 127 | 0 | 0 | 0 | 0 | 6.3 | 8.7 | 12.1 | 12.3 | 8.7 | 0 | 0 | 0 | 48.1 | 107.9 | -19.1 | 37.87% | 186.1 | WBS-101-171
1.1.13 | Study for sidetrack HB-180S | Eastgate | Capex | Low | Manager 04 | In negotiation | 0 | 138.8 | 129.6 | 184.4 | 84 | 112.8 | 212.8 | 199.7 | 159.4 | 238.6 | 215.5 | 155.6 | 268.4 | 381.2 | 571.9 | 609.7 | 1831.2 | 0 | 90.9 | 141.7 | 158 | 55.3 | 81.7 | 216 | 203 | 118.9 | 0 | 0 | 0 | 1065.5 | 1768.6 | -62.6 | 58.19% | 1505.3 | WBS-101-180 | Long-lead equipment ordered; delivery expected in Q3.
1.2 | Well workovers | [5 empty] | 0 | 0 | 84.8 | 144.5 | 313.1 | 454.9 | 386.1 | 472.8 | 531.8 | 485.3 | 534 | 380.7 | 84.8 | 912.5 | 1390.7 | 1400 | 3788 | 0 | 0 | 91.6 | 145.2 | 240.5 | 455.8 | 299.7 | 387.4 | 380.2 | 0 | 0 | 0 | 2000.4 | 3420.9 | -367.1 | 52.81% | 2181.2
1.2.1 | Upgrade of wellhead set 185 | Eastgate | Opex | Medium | Manager 22 | Planned | 0 | 0 | 0 | 0 | 0 | 68.9 | 68.5 | 53.7 | 52.7 | 26.6 | 61.4 | 60.1 | 0 | 68.9 | 174.9 | 148.1 | 391.9 | 0 | 0 | 0 | 0 | 0 | 67.8 | 60.4 | 30 | 50.4 | 0 | 0 | 0 | 208.6 | 337.8 | -54.1 | 53.23% | 66.3 | WBS-102-185 | Permit pending; spending moved to the second half of the year.
1.2.2 | Overhaul of workover rig campaign 186 | Corporate | Opex | Medium | Manager 20 | Planned | 0 | 0 | 0 | 0 | 111.7 | 71.8 | 67.8 | 48.8 | 91.6 | 97.6 | 109.7 | 78.5 | 0 | 183.5 | 208.2 | 285.8 | 677.5 | 0 | 0 | 0 | 0 | 94 | 59.2 | 63.1 | 48.2 | 65.4 | 0 | 0 | 0 | 329.9 | 627 | -50.5 | 48.69% | 162.2 | WBS-102-186 | Permit pending; spending moved to the second half of the year.
1.2.3 | Study for workover rig campaign 187 | Silver Creek | Opex | High | Manager 14 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-102-187
1.2.4 | Study for artificial lift at HB-191 | Silver Creek | Opex | Medium | Manager 01 | In negotiation | 0 | 0 | 0 | 0 | 0 | 132.6 | 76.9 | 123.9 | 139.6 | 135.2 | 123.6 | 125.8 | 0 | 132.6 | 340.4 | 384.6 | 857.6 | 0 | 0 | 0 | 0 | 0 | 144.6 | 74.2 | 86.5 | 115.8 | 0 | 0 | 0 | 421.1 | 880.9 | 23.3 | 49.1% | 1142.4 | WBS-102-191
1.2.5 | Replacement of wellhead set 195 | Cedar Point | Opex | Medium | Manager 11 | Planned | 0 | 0 | 84.8 | 117.5 | 170.3 | 152.2 | 154.1 | 235.9 | 234.9 | 203.4 | 218.5 | 94.6 | 84.8 | 440 | 624.9 | 516.5 | 1666.2 | 0 | 0 | 91.6 | 117.8 | 126.3 | 150.7 | 86.5 | 212.3 | 136.3 | 0 | 0 | 0 | 921.5 | 1387.7 | -278.5 | 55.31% | 675.3 | WBS-102-195
1.2.6 | Upgrade of workover rig campaign 199 | Harbor Basin | Opex | Medium | Manager 12 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 131.8 | WBS-102-199 | Cancelled in 2026; kept for the audit trail.
1.2.7 | Overhaul of workover rig campaign 203 | Harbor Basin | Opex | High | Manager 22 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-102-203
1.2.8 | Overhaul of wellhead set 212 | Eastgate | Opex | High | Manager 14 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-102-212 | On hold until the 2028 budget review.
1.2.9 | Overhaul of wellhead set 218 | Eastgate | Opex | Medium | Manager 07 | In negotiation | 0 | 0 | 0 | 27 | 31.1 | 29.4 | 18.8 | 10.5 | 13 | 22.5 | 20.8 | 21.7 | 0 | 87.5 | 42.3 | 65 | 194.8 | 0 | 0 | 0 | 27.4 | 20.2 | 33.5 | 15.5 | 10.4 | 12.3 | 0 | 0 | 0 | 119.3 | 187.5 | -7.3 | 61.24% | 3.2 | WBS-102-218
1.3 | Field facilities | [5 empty] | 106.9 | 121.8 | 113.6 | 222.9 | 245.8 | 353.2 | 347.4 | 283.6 | 263.4 | 354.5 | 304 | 346 | 342.3 | 821.9 | 894.4 | 1004.5 | 3063.1 | 97.1 | 123.1 | 97.9 | 200.8 | 186.9 | 363.9 | 284.6 | 217.3 | 208.9 | 33.7 | 8.6 | 15.8 | 1838.6 | 2816.2 | -246.9 | 60.02% | 2316.1
1.3.1 | Upgrade of flare system 221 | Cedar Point | Capex | Medium | Manager 14 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-103-221 | Deferred: waiting for partner approval.
1.3.2 | Study for separator train 223 | Harbor Basin | Capex | Medium | Manager 19 | In negotiation | 0 | 0 | 0 | 22.8 | 30.6 | 38.3 | 19.7 | 31 | 43.4 | 61.1 | 34.9 | 26.7 | 0 | 91.7 | 94.1 | 122.7 | 308.5 | 0 | 0 | 0 | 24.8 | 34.4 | 38.6 | 20 | 19.5 | 30.6 | 0 | 0 | 0 | 167.9 | 287.9 | -20.6 | 54.42% | 188.3 | WBS-103-223
1.3.3 | New separator train 228 | Silver Creek | Capex | High | Manager 05 | Tender | 0 | 0 | 0 | 0 | 0 | 60.5 | 65.7 | 98.3 | 71.4 | 67.6 | 72.6 | 66.6 | 0 | 60.5 | 235.4 | 206.8 | 502.7 | 0 | 0 | 0 | 0 | 0 | 60.6 | 54.1 | 77.9 | 56.1 | 0 | 0 | 0 | 248.7 | 451.6 | -51.1 | 49.47% | 272 | WBS-103-228 | Design approved; construction starts after the rainy season.
1.3.4 | New gathering line GL-233 | Silver Creek | Capex | Medium | Manager 23 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.7 | 8.6 | 15.8 | 58.1 | 117.4 | 117.4 | 0% | 0 | WBS-103-233
1.3.5 | Overhaul of separator train 240 | Eastgate | Capex | Medium | Manager 03 | In negotiation | 0 | 0 | 0 | 13 | 23.8 | 25.7 | 23.9 | 12.2 | 23.3 | 23.8 | 25.6 | 20 | 0 | 62.5 | 59.4 | 69.4 | 191.3 | 0 | 0 | 0 | 8.1 | 18.1 | 20.8 | 24.9 | 7.9 | 20.1 | 0 | 0 | 0 | 99.9 | 160.9 | -30.4 | 52.22% | 112.5 | WBS-103-240 | Contractor mobilised; schedule confirmed with operations.
1.3.6 | Study for gathering line GL-245 | Eastgate | Capex | Medium | Manager 01 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 14.5 | WBS-103-245 | Cancelled in 2026; kept for the audit trail.
1.3.7 | Upgrade of flare system 250 | Silver Creek | Capex | High | Manager 14 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 236.6 | WBS-103-250 | Cancelled in 2026; kept for the audit trail.
1.3.8 | Study for gathering line GL-258 | Silver Creek | Capex | Low | Manager 20 | Planned | 0 | 21.6 | 18.2 | 26.1 | 69 | 41.3 | 64 | 62.1 | 51.4 | 39.8 | 30.4 | 45.4 | 39.8 | 136.4 | 177.5 | 115.6 | 469.3 | 0 | 19.5 | 13.3 | 20.7 | 58.6 | 32.9 | 52 | 42.1 | 39.3 | 0 | 0 | 0 | 278.4 | 373.9 | -95.4 | 59.32% | 430.7 | WBS-103-258
1.3.9 | Expansion of flare system 266 | Silver Creek | Capex | Medium | Manager 02 | Planned | 34.3 | 40.4 | 31.3 | 51 | 71.3 | 52.6 | 58.2 | 37.2 | 26.4 | 25.8 | 53.9 | 69 | 106 | 174.9 | 121.8 | 148.7 | 551.4 | 38.8 | 36.8 | 23.1 | 55.7 | 43.5 | 57.8 | 55.1 | 33.7 | 28.9 | 0 | 0 | 0 | 373.4 | 535.6 | -15.8 | 67.72% | 529 | WBS-103-266
1.3.10 | Overhaul of separator train 275 | Cedar Point | Capex | Medium | Manager 07 | In negotiation | 72.6 | 59.8 | 64.1 | 110 | 51.1 | 134.8 | 115.9 | 42.8 | 47.5 | 136.4 | 86.6 | 118.3 | 196.5 | 295.9 | 206.2 | 341.3 | 1039.9 | 58.3 | 66.8 | 61.5 | 91.5 | 32.3 | 153.2 | 78.5 | 36.2 | 33.9 | 0 | 0 | 0 | 612.2 | 888.9 | -151 | 58.87% | 532.5 | WBS-103-275
2 | MIDSTREAM — PIPELINES AND STORAGE | [5 empty] | 471.8 | 501.6 | 1001.1 | 952.5 | 1036.4 | 1126 | 1195.7 | 979.3 | 1112.5 | 1368.6 | 1074.7 | 1533.4 | 1974.5 | 3114.9 | 3287.5 | 3976.7 | 12353.6 | 316.5 | 376 | 904.9 | 772.7 | 846.5 | 1014.3 | 964 | 810.4 | 895.4 | 0 | 0 | 0 | 6900.7 | 11093.7 | -1259.9 | 55.86% | 7104.8
2.1 | Pipeline integrity | [5 empty] | 60.5 | 61.9 | 458 | 470.4 | 391 | 717.9 | 530 | 468.4 | 521 | 732.4 | 475.1 | 785.4 | 580.4 | 1579.3 | 1519.4 | 1992.9 | 5672 | 63.3 | 66.4 | 455 | 360.9 | 357.1 | 672.4 | 434 | 349.8 | 436.5 | 0 | 0 | 0 | 3195.4 | 5299.7 | -372.3 | 56.34% | 3255.4
2.1.1 | Overhaul of cathodic protection zone 283 | Eastgate | Capex | Low | Manager 03 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-201-283 | Deferred: waiting for partner approval.
2.1.2 | Upgrade of cathodic protection zone 287 | Cedar Point | Capex | Low | Manager 24 | Signed | 0 | 0 | 18.4 | 24.8 | 20.2 | 10.4 | 16.5 | 19 | 18.1 | 14.7 | 10.4 | 27.3 | 18.4 | 55.4 | 53.6 | 52.4 | 179.8 | 0 | 0 | 11.1 | 25.2 | 16.9 | 10.9 | 10.5 | 21.2 | 13.7 | 0 | 0 | 0 | 109.5 | 164.1 | -15.7 | 60.9% | 77.9 | WBS-201-287
2.1.3 | Expansion of cathodic protection zone 293 | Silver Creek | Capex | Medium | Manager 08 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-201-293
2.1.4 | Overhaul of cathodic protection zone 300 | Cedar Point | Capex | Low | Manager 04 | Tender | 0 | 0 | 92.3 | 106.4 | 134.5 | 206 | 108.3 | 69.7 | 183.4 | 218.2 | 120.1 | 251.6 | 92.3 | 446.9 | 361.4 | 589.9 | 1490.5 | 0 | 0 | 88.4 | 63.5 | 129.5 | 192.2 | 97 | 52.9 | 112.3 | 0 | 0 | 0 | 735.8 | 1335.7 | -154.8 | 49.37% | 1483.6 | WBS-201-300 | Carry-over from 2026; final invoices only.
2.1.5 | Study for cathodic protection zone 303 | Eastgate | Capex | Medium | Manager 21 | In negotiation | 0 | 0 | 0 | 0 | 0 | 121.5 | 132.2 | 66.8 | 109.3 | 213.9 | 130.1 | 168 | 0 | 121.5 | 308.3 | 512 | 941.8 | 0 | 0 | 0 | 0 | 0 | 111.4 | 105.7 | 47 | 91 | 0 | 0 | 0 | 355.1 | 957 | 15.2 | 37.7% | 1060.9 | WBS-201-303
2.1.6 | Study for pipeline section PL-309 | Corporate | Capex | Medium | Manager 07 | In negotiation | 0 | 0 | 223.3 | 196.2 | 85.4 | 250.5 | 126.9 | 234.8 | 132.6 | 153.3 | 151.8 | 187.2 | 223.3 | 532.1 | 494.3 | 492.3 | 1742 | 0 | 0 | 218 | 189.6 | 67.3 | 228 | 89.1 | 164.6 | 137.5 | 0 | 0 | 0 | 1094.1 | 1655.9 | -86.1 | 62.81% | 208.9 | WBS-201-309
2.1.7 | Replacement of inline inspection run 311 | Silver Creek | Capex | Low | Manager 03 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-201-311
2.1.8 | Overhaul of pipeline section PL-319 | Corporate | Capex | Medium | Manager 15 | Signed | 0 | 0 | 0 | 0 | 13.2 | 22 | 24.2 | 16.5 | 25.8 | 15.5 | 25.4 | 15 | 0 | 35.2 | 66.5 | 55.9 | 157.6 | 0 | 0 | 0 | 0 | 8.6 | 14.3 | 13.3 | 9.2 | 26.8 | 0 | 0 | 0 | 72.2 | 119.6 | -38 | 45.81% | 139.5 | WBS-201-319
2.1.9 | Overhaul of pipeline section PL-323 | Harbor Basin | Capex | High | Manager 01 | Signed | 60.5 | 61.9 | 124 | 143 | 137.7 | 107.5 | 121.9 | 61.6 | 51.8 | 116.8 | 37.3 | 136.3 | 246.4 | 388.2 | 235.3 | 290.4 | 1160.3 | 63.3 | 66.4 | 137.5 | 82.6 | 134.8 | 115.6 | 118.4 | 54.9 | 55.2 | 0 | 0 | 0 | 828.7 | 1067.4 | -92.9 | 71.42% | 284.6 | WBS-201-323 | Permit pending; spending moved to the second half of the year.
2.2 | Storage terminals | [5 empty] | 411.3 | 439.7 | 543.1 | 482.1 | 645.4 | 408.1 | 665.7 | 510.9 | 591.5 | 636.2 | 599.6 | 748 | 1394.1 | 1535.6 | 1768.1 | 1983.8 | 6681.6 | 253.2 | 309.6 | 449.9 | 411.8 | 489.4 | 341.9 | 530 | 460.6 | 458.9 | 0 | 0 | 0 | 3705.3 | 5794 | -887.6 | 55.46% | 3849.4
2.2.1 | Replacement of loading bay 326 | Silver Creek | Capex | Low | Manager 04 | Planned | 0 | 29.5 | 69.3 | 50.1 | 62.9 | 71.8 | 27.7 | 55.5 | 48.9 | 69.4 | 45.4 | 62.3 | 98.8 | 184.8 | 132.1 | 177.1 | 592.8 | 0 | 20.3 | 58.5 | 31.3 | 54.3 | 60.3 | 15.9 | 55.6 | 51.3 | 0 | 0 | 0 | 347.5 | 534 | -58.8 | 58.62% | 742.7 | WBS-202-326 | Scope reduced after technical review; savings reallocated.
2.2.2 | Replacement of loading bay 330 | Cedar Point | Capex | Low | Manager 04 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-330
2.2.3 | Study for loading bay 335 | Silver Creek | Capex | Medium | Manager 20 | Planned | 0 | 0 | 81.6 | 71.2 | 79 | 50.8 | 73.9 | 126.1 | 38 | 109.6 | 89 | 141.4 | 81.6 | 201 | 238 | 340 | 860.6 | 0 | 0 | 44.9 | 66.2 | 66.1 | 58.3 | 84.9 | 141.9 | 32.4 | 0 | 0 | 0 | 494.7 | 781.6 | -79 | 57.48% | 995.3 | WBS-202-335 | Carry-over from 2026; final invoices only.
2.2.4 | Upgrade of tank T-340 | Corporate | Capex | Medium | Manager 17 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-340
2.2.5 | Overhaul of loading bay 347 | Eastgate | Capex | Medium | Manager 10 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-347
2.2.6 | Study for metering skid 356 | Eastgate | Capex | Medium | Manager 22 | Signed | 217.7 | 169.1 | 173.9 | 218.7 | 188.8 | 120.2 | 253.5 | 187.2 | 231.2 | 254.9 | 230.5 | 254.7 | 560.7 | 527.7 | 671.9 | 740.1 | 2500.4 | 133.5 | 110.1 | 142.3 | 200 | 120 | 70.3 | 160.4 | 169 | 159.3 | 0 | 0 | 0 | 1264.9 | 2144.1 | -356.3 | 50.59% | 697.7 | WBS-202-356 | Carry-over from 2026; final invoices only.
2.2.7 | Upgrade of loading bay 364 | Eastgate | Capex | Low | Manager 10 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-364
2.2.8 | Replacement of tank T-366 | Harbor Basin | Capex | High | Manager 20 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-366
2.2.9 | New tank T-371 | Harbor Basin | Capex | Low | Manager 09 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-371
2.2.10 | Study for tank T-378 | Harbor Basin | Capex | Medium | Manager 21 | In negotiation | 9.5 | 14 | 23.9 | 19.9 | 24.2 | 20.6 | 11 | 29.9 | 21.4 | 13.3 | 29.5 | 18.8 | 47.4 | 64.7 | 62.3 | 61.6 | 236 | 5.7 | 15.9 | 22.6 | 17.6 | 13.5 | 16.5 | 10 | 16.6 | 12.4 | 0 | 0 | 0 | 130.8 | 189.6 | -46.4 | 55.42% | 240.6 | WBS-202-378
2.2.11 | Upgrade of metering skid 383 | Silver Creek | Capex | Low | Manager 12 | Tender | 184.1 | 227.1 | 194.4 | 122.2 | 243.8 | 84.4 | 240.9 | 85.5 | 204.4 | 126.3 | 143 | 225 | 605.6 | 450.4 | 530.8 | 494.3 | 2081.1 | 114 | 163.3 | 181.6 | 96.7 | 197.9 | 79.5 | 205.4 | 59.6 | 173.8 | 0 | 0 | 0 | 1271.8 | 1752.5 | -328.6 | 61.11% | 958 | WBS-202-383 | Contractor mobilised; schedule confirmed with operations.
2.2.12 | Replacement of metering skid 388 | Harbor Basin | Capex | High | Manager 07 | In negotiation | 0 | 0 | 0 | 0 | 46.7 | 60.3 | 58.7 | 26.7 | 47.6 | 62.7 | 62.2 | 45.8 | 0 | 107 | 133 | 170.7 | 410.7 | 0 | 0 | 0 | 0 | 37.6 | 57 | 53.4 | 17.9 | 29.7 | 0 | 0 | 0 | 195.6 | 392.2 | -18.5 | 47.63% | 215.1 | WBS-202-388
2.2.13 | Expansion of loading bay 390 | Eastgate | Capex | High | Manager 23 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-202-390 | On hold until the 2028 budget review.
3 | POWER AND UTILITIES | [5 empty] | 50.1 | 413.6 | 511.1 | 482.2 | 804.9 | 1033.9 | 1015.5 | 883.6 | 1200.4 | 1003.8 | 856.7 | 989.1 | 974.8 | 2321 | 3099.5 | 2849.6 | 9244.9 | 37.6 | 431.8 | 457.6 | 440.7 | 681.1 | 840.5 | 890.9 | 750.1 | 1054.2 | 31.8 | 25.3 | 14.1 | 5655.7 | 8565.6 | -679.3 | 61.18% | 6093.6
3.1 | Gas-fired power unit | [5 empty] | 0 | 253.4 | 233 | 176.8 | 119.2 | 166.9 | 131.3 | 161.5 | 345 | 150.1 | 182.5 | 265.8 | 486.4 | 462.9 | 637.8 | 598.4 | 2185.5 | 0 | 269.5 | 227.3 | 175.1 | 81.1 | 156.6 | 100.6 | 140.6 | 281.9 | 0 | 0 | 0 | 1432.7 | 2034.1 | -151.4 | 65.55% | 1022
3.1.1 | New turbine unit G392 | Cedar Point | Capex | Medium | Manager 12 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-392
3.1.2 | Expansion of control room 395 | Corporate | Capex | High | Manager 22 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-395
3.1.3 | Replacement of turbine unit G403 | Harbor Basin | Capex | High | Manager 13 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-403
3.1.4 | Overhaul of turbine unit G410 | Harbor Basin | Capex | Medium | Manager 24 | In negotiation | 0 | 0 | 60.4 | 33 | 49.3 | 42.2 | 36.8 | 23.4 | 68.2 | 44.3 | 60.2 | 31 | 60.4 | 124.5 | 128.4 | 135.5 | 448.8 | 0 | 0 | 54.8 | 22.4 | 32 | 38.6 | 39 | 18.5 | 37.6 | 0 | 0 | 0 | 242.9 | 388.4 | -60.4 | 54.12% | 590.8 | WBS-301-410
3.1.5 | Study for control room 416 | Cedar Point | Capex | High | Manager 07 | Planned | 0 | 253.4 | 172.6 | 143.8 | 69.9 | 104.9 | 75.3 | 111.9 | 248.4 | 76.9 | 109.1 | 220.5 | 426 | 318.6 | 435.6 | 406.5 | 1586.7 | 0 | 269.5 | 172.5 | 152.7 | 49.1 | 99.6 | 49.1 | 96.6 | 212.7 | 0 | 0 | 0 | 1101.8 | 1496.4 | -90.3 | 69.44% | 184.4 | WBS-301-416 | Contractor mobilised; schedule confirmed with operations.
3.1.6 | Upgrade of turbine unit G424 | Eastgate | Capex | Low | Manager 07 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-424
3.1.7 | Study for heat recovery boiler 429 | Harbor Basin | Capex | Low | Manager 12 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-429
3.1.8 | Overhaul of control room 434 | Corporate | Capex | High | Manager 05 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 221.8 | WBS-301-434 | Cancelled in 2026; kept for the audit trail.
3.1.9 | Overhaul of heat recovery boiler 441 | Corporate | Capex | Medium | Manager 17 | Planned | 0 | 0 | 0 | 0 | 0 | 19.8 | 19.2 | 26.2 | 28.4 | 28.9 | 13.2 | 14.3 | 0 | 19.8 | 73.8 | 56.4 | 150 | 0 | 0 | 0 | 0 | 0 | 18.4 | 12.5 | 25.5 | 31.6 | 0 | 0 | 0 | 88 | 149.3 | -0.7 | 58.67% | 25 | WBS-301-441 | Cost estimate updated for steel prices (+6%).
3.1.10 | Replacement of heat recovery boiler 442 | Corporate | Capex | High | Manager 21 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-301-442
3.2 | Grid connections | [5 empty] | 12.7 | 116.9 | 234.4 | 183.2 | 442.7 | 482.6 | 448.8 | 325.1 | 408.5 | 400.6 | 313 | 406.3 | 364 | 1108.5 | 1182.4 | 1119.9 | 3774.8 | 8.3 | 124.8 | 183.9 | 160.1 | 359.5 | 369.9 | 417.2 | 281.2 | 363.8 | 0 | 0 | 0 | 2268.7 | 3385.3 | -389.5 | 60.1% | 2586.4
3.2.1 | Overhaul of transformer bank 443 | Harbor Basin | Capex | High | Manager 12 | Planned | 0 | 68.9 | 120.6 | 81.5 | 253.4 | 146.5 | 219.4 | 84.1 | 172.4 | 82.8 | 78.6 | 153.1 | 189.5 | 481.4 | 475.9 | 314.5 | 1461.3 | 0 | 77.8 | 89.6 | 72.2 | 171.6 | 98.9 | 212.6 | 81.4 | 143.4 | 0 | 0 | 0 | 947.5 | 1203 | -258.3 | 64.84% | 489.6 | WBS-302-443
3.2.2 | Study for overhead line OL-444 | Corporate | Capex | Medium | Manager 23 | Tender | 12.7 | 29.9 | 30.3 | 31.4 | 16.7 | 28.6 | 8.6 | 24 | 9.5 | 18.6 | 11.8 | 15.1 | 72.9 | 76.7 | 42.1 | 45.5 | 237.2 | 8.3 | 27.2 | 24.1 | 35.6 | 9.2 | 16.7 | 8 | 15.1 | 5.9 | 0 | 0 | 0 | 150.1 | 191.4 | -45.8 | 63.28% | 202.4 | WBS-302-444
3.2.3 | Study for transformer bank 449 | Eastgate | Capex | Low | Manager 14 | Tender | 0 | 0 | 0 | 0 | 0 | 36.3 | 40 | 26.5 | 54.8 | 63.8 | 40.4 | 59.8 | 0 | 36.3 | 121.3 | 164 | 321.6 | 0 | 0 | 0 | 0 | 0 | 28.9 | 27.7 | 17.9 | 40.7 | 0 | 0 | 0 | 115.2 | 309.6 | -12 | 35.82% | 34.7 | WBS-302-449
3.2.4 | Expansion of overhead line OL-453 | Harbor Basin | Capex | Medium | Manager 15 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 64.3 | WBS-302-453 | Cancelled in 2026; kept for the audit trail.
3.2.5 | Expansion of overhead line OL-462 | Cedar Point | Capex | Medium | Manager 16 | Signed | 0 | 0 | 0 | 0 | 0 | 57.6 | 50.4 | 37 | 53.5 | 49.5 | 64.7 | 62.4 | 0 | 57.6 | 140.9 | 176.6 | 375.1 | 0 | 0 | 0 | 0 | 0 | 33.4 | 56 | 28 | 59.9 | 0 | 0 | 0 | 177.3 | 371 | -4.1 | 47.27% | 165.6 | WBS-302-462
3.2.6 | Expansion of transformer bank 468 | Cedar Point | Capex | Low | Manager 04 | Signed | 0 | 0 | 0 | 0 | 21.7 | 52.9 | 55.9 | 53.8 | 47.9 | 34.5 | 50.5 | 55.6 | 0 | 74.6 | 157.6 | 140.6 | 372.8 | 0 | 0 | 0 | 0 | 24.7 | 55.6 | 55.1 | 37.2 | 50.8 | 0 | 0 | 0 | 223.4 | 341.8 | -31 | 59.92% | 417.9 | WBS-302-468 | Cost estimate updated for steel prices (+6%).
3.2.7 | Study for transformer bank 474 | Silver Creek | Capex | Medium | Manager 05 | Signed | 0 | 18.1 | 16 | 28.9 | 25.3 | 17.8 | 25.2 | 15.3 | 13.7 | 15.9 | 16 | 11.4 | 34.1 | 72 | 54.2 | 43.3 | 203.6 | 0 | 19.8 | 15 | 22.8 | 18.3 | 14 | 28.1 | 9.1 | 10.2 | 0 | 0 | 0 | 137.3 | 176.6 | -27 | 67.44% | 3.1 | WBS-302-474
3.2.8 | Upgrade of transformer bank 479 | Eastgate | Capex | Medium | Manager 15 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 207.7 | WBS-302-479 | Cancelled in 2026; kept for the audit trail.
3.2.9 | Overhaul of substation SS-486 | Eastgate | Capex | Medium | Manager 10 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-302-486
3.2.10 | New overhead line OL-487 | Cedar Point | Capex | High | Manager 06 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 105.8 | WBS-302-487 | Cancelled in 2026; kept for the audit trail.
3.2.11 | Expansion of transformer bank 491 | Silver Creek | Capex | Low | Manager 22 | Tender | 0 | 0 | 67.5 | 41.4 | 125.6 | 142.9 | 49.3 | 84.4 | 56.7 | 135.5 | 51 | 48.9 | 67.5 | 309.9 | 190.4 | 235.4 | 803.2 | 0 | 0 | 55.2 | 29.5 | 135.7 | 122.4 | 29.7 | 92.5 | 52.9 | 0 | 0 | 0 | 517.9 | 791.9 | -11.3 | 64.48% | 895.3 | WBS-302-491
3.3 | Water treatment | [5 empty] | 37.4 | 43.3 | 43.7 | 122.2 | 243 | 384.4 | 435.4 | 397 | 446.9 | 453.1 | 361.2 | 317 | 124.4 | 749.6 | 1279.3 | 1131.3 | 3284.6 | 29.3 | 37.5 | 46.4 | 105.5 | 240.5 | 314 | 373.1 | 328.3 | 408.5 | 31.8 | 25.3 | 14.1 | 1954.3 | 3146.2 | -138.4 | 59.5% | 2485.2
3.3.1 | Overhaul of injection pump set 497 | Harbor Basin | Capex | Medium | Manager 19 | In negotiation | 0 | 0 | 0 | 36.2 | 42.7 | 54.5 | 39.5 | 37.4 | 32.5 | 22.8 | 40.9 | 58.1 | 0 | 133.4 | 109.4 | 121.8 | 364.6 | 0 | 0 | 0 | 37.8 | 29.1 | 35.9 | 40.2 | 30.2 | 32.8 | 0 | 0 | 0 | 206 | 338.4 | -26.2 | 56.5% | 88.5 | WBS-303-497
3.3.2 | Study for injection pump set 498 | Cedar Point | Capex | Low | Manager 17 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 276.4 | WBS-303-498 | Cancelled in 2026; kept for the audit trail.
3.3.3 | Upgrade of reservoir 503 | Silver Creek | Capex | High | Manager 17 | Signed | 0 | 0 | 0 | 0 | 0 | 157 | 236.3 | 138.1 | 129.6 | 222.7 | 75.9 | 96.3 | 0 | 157 | 504 | 394.9 | 1055.9 | 0 | 0 | 0 | 0 | 0 | 120.4 | 181 | 118.9 | 91.3 | 0 | 0 | 0 | 511.6 | 966.8 | -89.1 | 48.45% | 917.8 | WBS-303-503
3.3.4 | Upgrade of injection pump set 510 | Harbor Basin | Capex | Low | Manager 01 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-303-510
3.3.5 | Upgrade of water plant module 513 | Eastgate | Capex | Medium | Manager 01 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.8 | 25.3 | 14.1 | 71.2 | 82.8 | 82.8 | 0% | 0 | WBS-303-513
3.3.6 | Overhaul of water plant module 521 | Cedar Point | Capex | Medium | Manager 21 | Planned | 0 | 0 | 0 | 20.5 | 21.4 | 13 | 18.9 | 28.1 | 31.9 | 20.4 | 13.1 | 11.4 | 0 | 54.9 | 78.9 | 44.9 | 178.7 | 0 | 0 | 0 | 15 | 22.7 | 13.8 | 10.7 | 21.5 | 32.7 | 0 | 0 | 0 | 116.4 | 163.9 | -14.8 | 65.14% | 11.6 | WBS-303-521 | Carry-over from 2026; final invoices only.
3.3.7 | Upgrade of reservoir 526 | Eastgate | Capex | High | Manager 13 | In negotiation | 0 | 0 | 0 | 0 | 146.5 | 89.1 | 96.2 | 155.3 | 220.5 | 145.1 | 176.8 | 110.6 | 0 | 235.6 | 472 | 432.5 | 1140.1 | 0 | 0 | 0 | 0 | 157.6 | 69.4 | 101.7 | 122.4 | 223.1 | 0 | 0 | 0 | 674.2 | 1106.2 | -33.9 | 59.14% | 1095.9 | WBS-303-526
3.3.8 | Upgrade of reservoir 530 | Cedar Point | Capex | High | Manager 22 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-303-530
3.3.9 | Expansion of injection pump set 531 | Silver Creek | Capex | Low | Manager 11 | Tender | 37.4 | 43.3 | 43.7 | 65.5 | 32.4 | 70.8 | 44.5 | 38.1 | 32.4 | 42.1 | 54.5 | 40.6 | 124.4 | 168.7 | 115 | 137.2 | 545.3 | 29.3 | 37.5 | 46.4 | 52.7 | 31.1 | 74.5 | 39.5 | 35.3 | 28.6 | 0 | 0 | 0 | 374.9 | 488.1 | -57.2 | 68.75% | 95 | WBS-303-531
3.3.10 | New reservoir 540 | Eastgate | Capex | High | Manager 17 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-303-540
4 | INFRASTRUCTURE AND LOGISTICS | [5 empty] | 0 | 102.7 | 137.2 | 90.6 | 105.1 | 89.9 | 79.2 | 117.8 | 120 | 95.2 | 37.6 | 113.3 | 239.9 | 285.6 | 317 | 246.1 | 1088.6 | 0 | 69.5 | 152.4 | 60.5 | 110.6 | 99.7 | 80 | 83.3 | 123 | 0 | 0 | 0 | 779 | 1050.7 | -37.9 | 71.56% | 1258.5
4.1 | Roads and bridges | [5 empty] | 0 | 102.7 | 137.2 | 90.6 | 105.1 | 89.9 | 79.2 | 117.8 | 120 | 95.2 | 37.6 | 113.3 | 239.9 | 285.6 | 317 | 246.1 | 1088.6 | 0 | 69.5 | 152.4 | 60.5 | 110.6 | 99.7 | 80 | 83.3 | 123 | 0 | 0 | 0 | 779 | 1050.7 | -37.9 | 71.56% | 1258.5
4.1.1 | Replacement of bridge B-545 | Harbor Basin | Capex | High | Manager 04 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-545 | On hold until the 2028 budget review.
4.1.2 | Upgrade of drainage works 547 | Harbor Basin | Capex | Low | Manager 05 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-547
4.1.3 | New access road R-549 | Silver Creek | Capex | High | Manager 24 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 202.9 | WBS-401-549 | Cancelled in 2026; kept for the audit trail.
4.1.4 | Overhaul of bridge B-551 | Eastgate | Capex | Low | Manager 10 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-551
4.1.5 | Replacement of access road R-554 | Cedar Point | Capex | Low | Manager 03 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-554
4.1.6 | Upgrade of drainage works 559 | Corporate | Capex | Medium | Manager 10 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-559
4.1.7 | Study for bridge B-568 | Silver Creek | Capex | Medium | Manager 22 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-401-568
4.1.8 | Replacement of access road R-574 | Eastgate | Capex | High | Manager 24 | Tender | 0 | 102.7 | 137.2 | 90.6 | 105.1 | 89.9 | 79.2 | 117.8 | 120 | 95.2 | 37.6 | 113.3 | 239.9 | 285.6 | 317 | 246.1 | 1088.6 | 0 | 69.5 | 152.4 | 60.5 | 110.6 | 99.7 | 80 | 83.3 | 123 | 0 | 0 | 0 | 779 | 1050.7 | -37.9 | 71.56% | 1055.6 | WBS-401-574
4.2 | Camps and offices | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
4.2.1 | Overhaul of regional office 581 | Cedar Point | Capex | Low | Manager 04 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-581
4.2.2 | Expansion of field camp block 590 | Cedar Point | Capex | Medium | Manager 21 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-590
4.2.3 | New regional office 592 | Cedar Point | Capex | High | Manager 02 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-592
4.2.4 | Study for field camp block 595 | Corporate | Capex | High | Manager 13 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-595
4.2.5 | Upgrade of warehouse 599 | Corporate | Capex | Low | Manager 15 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-599
4.2.6 | Study for field camp block 604 | Cedar Point | Capex | Medium | Manager 06 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-604
4.2.7 | Study for field camp block 605 | Harbor Basin | Capex | High | Manager 16 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-605
4.2.8 | Replacement of warehouse 613 | Eastgate | Capex | Medium | Manager 04 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-613
4.2.9 | New field camp block 622 | Eastgate | Capex | Medium | Manager 03 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-622
4.2.10 | Expansion of field camp block 631 | Harbor Basin | Capex | High | Manager 16 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-631
4.2.11 | Overhaul of field camp block 639 | Cedar Point | Capex | Low | Manager 18 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-402-639
5 | DIGITAL AND SAFETY | [5 empty] | 45.4 | 209.2 | 271.6 | 394 | 800.6 | 1093.2 | 957.2 | 906.9 | 1157.5 | 1047.7 | 1102.6 | 1190 | 526.2 | 2287.8 | 3021.6 | 3340.3 | 9175.9 | 43.2 | 202.8 | 219.4 | 273.9 | 698.4 | 929.4 | 800.8 | 743 | 1169.9 | 0 | 0 | 0 | 5080.8 | 8420.5 | -755.4 | 55.37% | 5864.1
5.1 | IT systems | [5 empty] | 29.9 | 56.4 | 135.3 | 294.9 | 443.6 | 744.1 | 697.5 | 496.3 | 684.9 | 770 | 715.4 | 857.9 | 221.6 | 1482.6 | 1878.7 | 2343.3 | 5926.2 | 31.2 | 40.5 | 116.6 | 185.5 | 380.7 | 687.9 | 533.3 | 472.8 | 722.8 | 0 | 0 | 0 | 3171.3 | 5586 | -340.2 | 53.51% | 4057
5.1.1 | Expansion of network site 645 | Eastgate | Capex | Medium | Manager 05 | In negotiation | 29.9 | 27.1 | 12.5 | 27 | 29.2 | 29.6 | 9 | 15.3 | 23.5 | 30 | 11.9 | 18.3 | 69.5 | 85.8 | 47.8 | 60.2 | 263.3 | 31.2 | 18.6 | 9.2 | 16.6 | 24.1 | 29.7 | 6.2 | 16 | 14.2 | 0 | 0 | 0 | 165.8 | 222 | -41.3 | 62.97% | 179.1 | WBS-501-645 | Carry-over from 2026; final invoices only.
5.1.2 | New ERP module 654 | Silver Creek | Capex | Low | Manager 11 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-501-654 | On hold until the 2028 budget review.
5.1.3 | Overhaul of network site 657 | Cedar Point | Capex | Medium | Manager 07 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-501-657 | Deferred: waiting for partner approval.
5.1.4 | Expansion of ERP module 665 | Silver Creek | Capex | High | Manager 12 | Signed | 0 | 0 | 0 | 0 | 0 | 191.2 | 188.4 | 98.6 | 140.3 | 238.9 | 161.2 | 224.3 | 0 | 191.2 | 427.3 | 624.4 | 1242.9 | 0 | 0 | 0 | 0 | 0 | 171.2 | 199 | 101.3 | 158.5 | 0 | 0 | 0 | 630 | 1207.2 | -35.7 | 50.69% | 297.4 | WBS-501-665 | Design approved; construction starts after the rainy season.
5.1.5 | Expansion of data centre rack 668 | Corporate | Capex | Low | Manager 21 | Signed | 0 | 0 | 58.8 | 62.1 | 66.1 | 23.3 | 35.2 | 67.1 | 71.2 | 68.9 | 19.6 | 30.3 | 58.8 | 151.5 | 173.5 | 118.8 | 502.6 | 0 | 0 | 55.3 | 38.7 | 59.3 | 15.5 | 39.1 | 37.6 | 54.3 | 0 | 0 | 0 | 299.8 | 431.8 | -70.8 | 59.65% | 5.7 | WBS-501-668
5.1.6 | Overhaul of data centre rack 672 | Cedar Point | Capex | Low | Manager 13 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-501-672
5.1.7 | Overhaul of ERP module 675 | Eastgate | Capex | High | Manager 21 | In negotiation | 0 | 0 | 46.2 | 58.1 | 120.8 | 41.9 | 63.5 | 91.3 | 117.2 | 121 | 142.5 | 119.9 | 46.2 | 220.8 | 272 | 383.4 | 922.4 | 0 | 0 | 38.8 | 41.1 | 111.4 | 34.5 | 44.2 | 93.2 | 134 | 0 | 0 | 0 | 497.2 | 896.2 | -26.2 | 53.9% | 741.6 | WBS-501-675
5.1.8 | Replacement of data centre rack 683 | Silver Creek | Capex | High | Manager 03 | In negotiation | 0 | 0 | 0 | 0 | 0 | 182.2 | 175.9 | 71.7 | 147.5 | 69.5 | 204.1 | 195.2 | 0 | 182.2 | 395.1 | 468.8 | 1046.1 | 0 | 0 | 0 | 0 | 0 | 192.7 | 99.6 | 73 | 158.9 | 0 | 0 | 0 | 524.2 | 1052.2 | 6.1 | 50.11% | 1518.9 | WBS-501-683 | Carry-over from 2026; final invoices only.
5.1.9 | Overhaul of data centre rack 692 | Corporate | Capex | High | Manager 10 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-501-692 | On hold until the 2028 budget review.
5.1.10 | Upgrade of network site 699 | Silver Creek | Capex | Medium | Manager 20 | Tender | 0 | 0 | 0 | 0 | 131.8 | 130.2 | 116 | 57.9 | 69.4 | 112.6 | 40.8 | 132.6 | 0 | 262 | 243.3 | 286 | 791.3 | 0 | 0 | 0 | 0 | 120.8 | 117.6 | 66.9 | 60.7 | 74.9 | 0 | 0 | 0 | 440.9 | 736.1 | -55.2 | 55.72% | 592.9 | WBS-501-699
5.1.11 | Upgrade of data centre rack 708 | Eastgate | Capex | Low | Manager 12 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 183.6 | WBS-501-708 | Cancelled in 2026; kept for the audit trail.
5.1.12 | Overhaul of network site 713 | Corporate | Capex | Low | Manager 23 | Tender | 0 | 29.3 | 17.8 | 11.4 | 8.2 | 17.8 | 16.6 | 25.5 | 24.5 | 13.1 | 9.5 | 22.7 | 47.1 | 37.4 | 66.6 | 45.3 | 196.4 | 0 | 21.9 | 13.3 | 9.6 | 9.2 | 17.6 | 18.2 | 29 | 24.3 | 0 | 0 | 0 | 143.1 | 187.8 | -8.6 | 72.86% | 166 | WBS-501-713
5.1.13 | Expansion of data centre rack 718 | Eastgate | Capex | Low | Manager 12 | Planned | 0 | 0 | 0 | 136.3 | 87.5 | 127.9 | 92.9 | 68.9 | 91.3 | 116 | 125.8 | 114.6 | 0 | 351.7 | 253.1 | 356.4 | 961.2 | 0 | 0 | 0 | 79.5 | 55.9 | 109.1 | 60.1 | 62 | 103.7 | 0 | 0 | 0 | 470.3 | 852.7 | -108.5 | 48.93% | 371.8 | WBS-501-718 | Design approved; construction starts after the rainy season.
5.2 | Safety and environment | [5 empty] | 15.5 | 152.8 | 136.3 | 99.1 | 357 | 349.1 | 259.7 | 410.6 | 472.6 | 277.7 | 387.2 | 332.1 | 304.6 | 805.2 | 1142.9 | 997 | 3249.7 | 12 | 162.3 | 102.8 | 88.4 | 317.7 | 241.5 | 267.5 | 270.2 | 447.1 | 0 | 0 | 0 | 1909.5 | 2834.5 | -415.2 | 58.76% | 1807.1
5.2.1 | Expansion of fire water ring 720 | Cedar Point | Capex | Low | Manager 10 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 227 | WBS-502-720 | Cancelled in 2026; kept for the audit trail.
5.2.2 | Replacement of fire water ring 725 | Silver Creek | Capex | Low | Manager 10 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-502-725
5.2.3 | Replacement of fire water ring 727 | Cedar Point | Capex | Medium | Manager 20 | Tender | 0 | 0 | 0 | 0 | 116.3 | 192.8 | 72.1 | 208.2 | 239.3 | 81.9 | 149.2 | 151.9 | 0 | 309.1 | 519.6 | 383 | 1211.7 | 0 | 0 | 0 | 0 | 95.2 | 137.6 | 78.9 | 124.7 | 239.2 | 0 | 0 | 0 | 675.6 | 1043.5 | -168.2 | 55.76% | 499.5 | WBS-502-727 | Contractor mobilised; schedule confirmed with operations.
5.2.4 | Replacement of gas detection zone 733 | Silver Creek | Capex | Low | Manager 16 | Signed | 0 | 22.6 | 29 | 23 | 24 | 11.4 | 13.2 | 19.8 | 24.2 | 28.8 | 29.9 | 22.4 | 51.6 | 58.4 | 57.2 | 81.1 | 248.3 | 0 | 25.9 | 17.5 | 14.1 | 27.4 | 8.8 | 9 | 15.1 | 23.4 | 0 | 0 | 0 | 141.2 | 235.3 | -13 | 56.87% | 37.7 | WBS-502-733
5.2.5 | Overhaul of gas detection zone 741 | Eastgate | Capex | Medium | Manager 13 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 253.4 | WBS-502-741 | Cancelled in 2026; kept for the audit trail.
5.2.6 | Expansion of emission monitor 743 | Eastgate | Capex | Low | Manager 17 | Tender | 15.5 | 17.2 | 10.9 | 11.7 | 9.9 | 12.4 | 28 | 22.2 | 16.6 | 15 | 20.1 | 25.9 | 43.6 | 34 | 66.8 | 61 | 205.4 | 12 | 12.2 | 8.5 | 6.7 | 9.2 | 11.4 | 27.5 | 23.4 | 11.9 | 0 | 0 | 0 | 122.8 | 174.7 | -30.7 | 59.79% | 76.9 | WBS-502-743
5.2.7 | Overhaul of fire water ring 751 | Silver Creek | Capex | Low | Manager 07 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-502-751
5.2.8 | Replacement of gas detection zone 759 | Corporate | Capex | Low | Manager 20 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-502-759
5.2.9 | Upgrade of fire water ring 762 | Eastgate | Capex | Medium | Manager 10 | Tender | 0 | 0 | 0 | 0 | 21.2 | 55 | 40.9 | 43.9 | 24 | 19.8 | 33.3 | 25.9 | 0 | 76.2 | 108.8 | 79 | 264 | 0 | 0 | 0 | 0 | 21.4 | 32.4 | 41.2 | 31.7 | 15.2 | 0 | 0 | 0 | 141.9 | 214.6 | -49.4 | 53.75% | 190.6 | WBS-502-762
5.2.10 | Upgrade of gas detection zone 770 | Eastgate | Capex | Medium | Manager 09 | Signed | 0 | 113 | 96.4 | 64.4 | 185.6 | 77.5 | 105.5 | 116.5 | 168.5 | 132.2 | 154.7 | 106 | 209.4 | 327.5 | 390.5 | 392.9 | 1320.3 | 0 | 124.2 | 76.8 | 67.6 | 164.5 | 51.3 | 110.9 | 75.3 | 157.4 | 0 | 0 | 0 | 828 | 1166.4 | -153.9 | 62.71% | 522 | WBS-502-770
6 | CORPORATE AND OTHER | [5 empty] | 0 | 0 | 108.6 | 214 | 192.6 | 318 | 307.6 | 288.1 | 412 | 320.4 | 297.5 | 308.7 | 108.6 | 724.6 | 1007.7 | 926.6 | 2767.5 | 0 | 0 | 102.9 | 197.8 | 161.1 | 305.6 | 280.4 | 233.4 | 344.7 | 0 | 0 | 0 | 1625.9 | 2520.4 | -247.1 | 58.75% | 1648.6
6.1 | Studies and engineering | [5 empty] | 0 | 0 | 108.6 | 214 | 192.6 | 318 | 307.6 | 288.1 | 412 | 320.4 | 297.5 | 308.7 | 108.6 | 724.6 | 1007.7 | 926.6 | 2767.5 | 0 | 0 | 102.9 | 197.8 | 161.1 | 305.6 | 280.4 | 233.4 | 344.7 | 0 | 0 | 0 | 1625.9 | 2520.4 | -247.1 | 58.75% | 1648.6
6.1.1 | New feasibility study 772 | Cedar Point | Opex | Medium | Manager 23 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 224.1 | WBS-601-772 | Cancelled in 2026; kept for the audit trail.
6.1.2 | Overhaul of survey 779 | Eastgate | Opex | High | Manager 21 | Planned | 0 | 0 | 0 | 126.1 | 43.4 | 38.7 | 85.6 | 42.3 | 138.8 | 67.3 | 56.6 | 58.9 | 0 | 208.2 | 266.7 | 182.8 | 657.7 | 0 | 0 | 0 | 109.7 | 41.9 | 40.4 | 86.6 | 40 | 94.1 | 0 | 0 | 0 | 412.7 | 586.7 | -71 | 62.75% | 49.1 | WBS-601-779
6.1.3 | Replacement of front-end design 782 | Corporate | Opex | Medium | Manager 01 | Tender | 0 | 0 | 47 | 64 | 95.4 | 67.1 | 89.9 | 94.6 | 118.3 | 78.5 | 49.8 | 141.4 | 47 | 226.5 | 302.8 | 269.7 | 846 | 0 | 0 | 52.8 | 67.9 | 86.4 | 57.5 | 94.3 | 52.8 | 131.8 | 0 | 0 | 0 | 543.5 | 827.6 | -18.4 | 64.24% | 222 | WBS-601-782
6.1.4 | Overhaul of front-end design 784 | Silver Creek | Opex | Low | Manager 16 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-601-784
6.1.5 | New feasibility study 787 | Corporate | Opex | Low | Manager 22 | Tender | 0 | 0 | 61.6 | 23.9 | 53.8 | 55.7 | 69.1 | 32.6 | 59.5 | 42 | 40.7 | 45.4 | 61.6 | 133.4 | 161.2 | 128.1 | 484.3 | 0 | 0 | 50.1 | 20.2 | 32.8 | 42.6 | 47.7 | 35.6 | 59 | 0 | 0 | 0 | 288 | 392.7 | -91.6 | 59.47% | 144.9 | WBS-601-787 | Scope reduced after technical review; savings reallocated.
6.1.6 | Overhaul of feasibility study 789 | Corporate | Opex | Low | Manager 11 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 110.7 | WBS-601-789 | Cancelled in 2026; kept for the audit trail.
6.1.7 | Upgrade of front-end design 792 | Harbor Basin | Opex | Medium | Manager 07 | Planned | 0 | 0 | 0 | 0 | 0 | 134.3 | 37.7 | 105.3 | 81.6 | 113.7 | 141.9 | 50.3 | 0 | 134.3 | 224.6 | 305.9 | 664.8 | 0 | 0 | 0 | 0 | 0 | 147.4 | 28.5 | 90.7 | 50.3 | 0 | 0 | 0 | 316.9 | 606.3 | -58.5 | 47.67% | 818.6 | WBS-601-792 | Long-lead equipment ordered; delivery expected in Q3.
6.1.8 | Overhaul of front-end design 799 | Cedar Point | Opex | Low | Manager 23 | Tender | 0 | 0 | 0 | 0 | 0 | 22.2 | 25.3 | 13.3 | 13.8 | 18.9 | 8.5 | 12.7 | 0 | 22.2 | 52.4 | 40.1 | 114.7 | 0 | 0 | 0 | 0 | 0 | 17.7 | 23.3 | 14.3 | 9.5 | 0 | 0 | 0 | 64.8 | 107.1 | -7.6 | 56.5% | 79.2 | WBS-601-799 | Scope reduced after technical review; savings reallocated.
6.1.9 | Overhaul of front-end design 806 | Corporate | Opex | High | Manager 11 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-601-806
6.2 | Legacy claims | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
6.2.1 | Replacement of contract claim 810 | Harbor Basin | Capex | Low | Manager 18 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-810
6.2.2 | New warranty case 819 | Cedar Point | Capex | Medium | Manager 04 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-819
6.2.3 | Overhaul of contract claim 822 | Corporate | Capex | Medium | Manager 04 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-822
6.2.4 | Study for land settlement 826 | Silver Creek | Capex | Low | Manager 13 | Signed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-826
6.2.5 | Upgrade of warranty case 827 | Eastgate | Capex | Low | Manager 15 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-827
6.2.6 | Expansion of land settlement 836 | Harbor Basin | Capex | Medium | Manager 02 | Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-836
6.2.7 | Replacement of land settlement 845 | Corporate | Capex | Medium | Manager 09 | In negotiation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | WBS-602-845
| GRAND TOTAL | [5 empty] | 798.3 | 1567.5 | 2587.4 | 3015.4 | 4062.1 | 5068.8 | 4853.8 | 4803.8 | 5525 | 5490.2 | 4928.6 | 5611.6 | 4953.2 | 12146.3 | 15182.6 | 16030.4 | 48312.5 | 620.7 | 1352.6 | 2373.2 | 2499.2 | 3338.7 | 4443.2 | 4117.9 | 3956.3 | 4777.3 | 102.8 | 54.7 | 69.4 | 27706 | 44057.5 | -4255 | 57.35% | 32995.4
Note on AL18: Forecast includes the approved change order.
Note on AL45: Forecast includes the approved change order.
Note on AL65: Forecast includes the approved change order.
Note on AL84: Forecast includes the approved change order.